Ministry of Labor, Health And Social Affairs

Georgian Avian Influenza Preparadness and Response Operational Plan

2009

Georgian Avian Influenza Preparadness and Response Operational Plan

Efficiency of pandemic preparedness and response measures for ensuring healthcare for Georgian population and mitigating the harm caused by pandemic largely depends on the possible adequacy of these measures and on technical and economical capacities for their implementation. These measures and actions shall also be ethically sound and acceptable for the society. General public shall be thoroughly informed regarding the actions planed and implemented by the government. Taking unethical, disproportionate and inadequate measures, or implementing the planned actions untimely – either too prematurely or too late, - may severely harm the health of population and economy, and lead to undesirable social consequences and loss of trust from public.

Considering the abovementioned, on the one hand, the government in often instances will have to respond and take measures under the conditions of the insufficient or rapidly changing information regarding the characteristics of pandemic influenza, clinical and epidemiological portrait of the disease and its possible inpacts during the pre-pandemic and pandemic periods. During the response and thereafter the content and the scope of various healthcare and organizational structural measures will be adjusted along with the evolution of pandemics, and obtaining the additional information regarding the character of the pandemics and the extent of its impact, which makes it difficult to plan in detail preparedness and response mechanisms and actions in advance.

On the other hand, in the modern world, emergence of new pandemic virus in any, even most remote area of the world may lead to the cases of infections from this virus in Georgia within one-two months period from the appiarence of the virus. Furthermore, the situation may be worsened due to the fact, that disease may develop into full-scale epidemics in Georgia within a period of five to six weeks from the first registered case of infection from the new virus, which decreases the chances to collect in this short period of time comprehensive epidemiological and scientific data regarding the new pandemic virus, providing the base for the assumptions crucial for preparedness and response plan. This in turn stresses the need for preliminary planning and rapid operational response enabled through developing flexible mechanisms, which will allow public and private institutions involved in the response to timely and efficiently revise and improve planed measures, actions and procedures along with the increase of the availability of information regarding the pandemic and the experience accumulated throughout the process of ensuring preparedness and response. For the purpose of such a planning, attached is the table with key actions and decisions listed, the need of which is anticipated during the pre-pandemic and pandemic phases and during the various levels of national alert and which make up the basis of pandemic preparedness and response operational plan. The role and responsibilities of key public institutions in implementing these actions and decision-making is also defined. This operational plan is not and cannot be exhaustive, as it is not possible to perfectly model the anticipated impacts of epidemics and thus, national and local response actions shall be based on practical data and experience on pandemic’s characteristics and severity, and effectiveness, impact and benefit of taken measures.

| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  | Critical information/action | Primary source of information |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WHO Phase 3 | Governmental commission | MoLHSA | MoA | Local authorities | Other |  |  |
| Monitor the spread of influenza in Georgia and assess the intervention strategy |  |  |  |  |  | Location, extent and impact of the disease spread on global level | MoLHSA, international Partners |
| Run/adjust the surveillance system and international cooperation |  |  |  |  |  | Epidemiological surveillance records | MoLHSA, MoA, WHO |
| Set up a commission/permanent team of specialists and experts |  |  |  |  |  | Pandemic virus characteristics, impact and spread | WHO, US and European CDCs, MoLHSA |
| Assess pandemic preparedness and response capacities and competences in critical infrastructures and define priorities on national and local levels |  |  |  |  | All participating parties | Official records, memos | Key public service providers |
| Develop/revise advices for travelers if needed |  |  |  |  | MIA | Virus spread and impact | MoLHSA, other international partners |

| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  | Critical information/action | Primary source of information |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WHO Phase 4 Alert level 1 in Georgia (Cases registered only outside Georgia) | Governmental commission | MoLHSA | MoA | Local authorities | Other |  |  |
| Activate emergency situations management, control and coordination mechanisms |  |  |  |  |  | Monitoring of national response | WHO/MoLHSA |
| Assess global situation on pandemic spread |  |  |  |  |  | International records | WHO and international partners |
| Revise the risk and impact assessment for disease spread |  |  |  |  |  | Spread and extent of morbidity and mortality | WHO/MoLHSA |
| Revise/intensify and focus on surveillance and research guidance and procedures |  |  |  |  |  | Monitoring and surveillance records | WHO/MoLHSA |
| Revise research and management procedures for suspect cases of the disease |  |  |  |  |  | Global epidemiological situation | WHO/MoLHSA |
| Develop/revise informational bulletins for travelers, including the assessment of the rationale for travel and transport restrictions |  |  |  |  | MoEA; MIA; | Global epidemiological situation | WHO/MoLHSA |
| Revise underlying assumptions for pandemic preparedness and response planning |  |  |  |  | Group of experts | Pandemic virus characteristics | WHO/US and European CDCs/ MoLHSA |
| Revise directives and guidelines developed in poultry and cattle-breeding sectors |  |  |  |  |  | Information about the source and the impact of pandemic virus | OIE/WHO |
| Revise/test medical, social and key public service plans |  |  |  |  | Relevant ministries and agencies |  | WHO/MoLHSA |
| Replenish the national strategic stockpile with pre-pandemic vaccines, antivirals, antibiotics and other medical materials and protective means; develop/test supply and distribution systems |  |  |  |  |  | Assess anticipated impact on health | WHO/MoLHSA/ Expert group |
| Test the mechanisms for data collection, exchange and coordination |  |  |  |  |  | List of agreed data and the database | Emergency situations agency |
| Evaluate the progress in development of pandemic vaccine and review Georgian procurement capacities |  |  |  |  |  | Identify pandemic virus subgroup and define its characteristics. Data from the research and vaccine producers | WHO, US and European CDCs/ MoLHSA/Expert group |
| Plan for the management of possible increased mortality |  |  |  |  |  | Audit | Local authorities |

| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  | Critical information/action | Primary source of information |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WHO Phase 5 Alert level 1 in Georgia (Cases registered only outside Georgia) | Governmental commission | MoLHSA | MoA | Local authorities | Other |  |  |
| Revise mechanisms for the assessment of risk and impact of disease spread and international and regional coordination |  |  |  |  | Relevant agencies | Epidemiological and general impact from pandemic influenza | WHO and international partners/MoLHSA |
| Prepare governmental procedures and mechanisms for emergency management |  |  |  |  |  | Information on global spread of disease | WHO and international partners |
| Revise the assessment for risk and impact of disease spread |  |  |  |  |  | Information on global spread of disease | WHO/MoLHSA |
| Revise underlying assumptions for pandemic preparedness and response planning and develop/revise appropriate interventions |  |  |  |  |  | Information on global spread of disease | WHO/MoLHSA |
| Develop/revise advice/information bulletins for travelers, including the assessment of the rationale for travel and transport restrictions (or screening) |  |  |  |  | MoE; MIA; | Practical data and modeling | WHO/MoLHSA/ Expert group |
| Prepare health institutions and medical personnel, reinforce surveillance and diagnostic capacities |  |  |  |  |  | Identification, diagnostic and treatment protocols | MoLHSA |
| Test medical, social and key public service plans |  |  |  |  | Relevant ministries and agencies |  | Governmental commission |
| Review the national strategic stockpile of pre-pandemic and pandemic vaccines, antivirals, antibiotics and other medical materials and protective means; develop and approve principals for distribution prioritization of the stock, if needed |  |  |  |  |  | Information and result of modeling on global spread of disease, and impact | Governmental commission |
| Set up a hotline for pandemic influenza and plan for and commence information and communication activities required for public awareness and preparedness |  |  |  |  |  | Governmental commission’s decision | WHO/Governmental commission/ Expert group |
| Evaluate the progress in development of pandemic vaccine and review Georgian procurement capacities |  |  |  |  |  | Identify pandemic virus subgroup and define its characteristics. Data from the research and vaccine producers | WHO, US and European CDCs/ MoLHSA/Expert group |
| Plan for the management of possible increased mortality |  |  |  |  |  | Audit | Governmental commission |

| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  |  |  |  |  | Critical information/action | Primary source of information |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WHO Phase 6 Alert level 1 in Georgia (Cases registered only outside Georgia) | Governmental commission |  | MoLHSA |  | MoA |  | Local authorities |  | Other |  |  |
| Define proportional response strategy |  |  |  |  |  |  |  |  |  | Information and prognosis on global spread of disease, its impact | WHO and international partners/MoLHSA |
| Prepare immediately response and reporting mechanisms |  |  |  |  |  |  |  |  |  | Routine reporting channels | WHO/MoLHSA |
| Finally revise advice/information bulletins for travelers |  |  |  |  |  |  |  |  | MIA | Pandemic practical data and modeling | WHO/MoLHSA |
| Decide upon travel and transport restrictions (or screening), establishing boarder measures |  |  |  |  |  |  |  |  | MIA | Pandemic practical data and modeling | WHO/MoLHSA |
| Develop information bulletin for students and their parents in case learning process in halted and schools are closed |  |  |  |  |  |  |  |  | Ministry of Education | Pandemic practical data | WHO/Expert group |
| Activate state commission for information and communication and commence public information champagne |  |  |  |  |  |  |  |  | Ministry of Education; Public broadcaster | Reports on communication strategy implementation | Governmental Commission/ MoLHSA |
| Review and revise criteria for patient management and hospitalization, as well as clinical guidance |  |  |  |  |  |  |  |  |  | Attained clinical data | WHO/ US and European CDCs/ MoLHSA |
| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  |  |  |  |  | Critical information/action | Primary source of information |
| WHO Phase 6 Alert level 2 in Georgia (Virus isolated in Georgia) | Governmental commission |  |  | MoLHSA |  | MoA |  | Local authorities | Other |  |  |
| Revise threat assessment and implement appropriate broad response measures |  |  |  |  |  |  |  |  | Relevant ministries and agencies | Pandemic progress and prognoses | MoLHSA |
| Mobilize totally healthcare and other services, contract selected referral health centers |  |  |  |  |  |  |  |  |  | Pandemic progress and prognoses | MoLHSA |
| Intensify surveillance, viral diagnostic, research and reporting procedures |  |  |  |  |  |  |  |  |  | Pandemic progress and prognoses | MoLHSA |
| Activate hot-lines on regional and rayon levels |  |  |  |  |  |  |  |  |  | Decision of Governmental commission | MoLHSA |
| Authorize healthcare services to exclusively proceed to emergency hospitalization |  |  |  |  |  |  |  |  |  | Pandemic progress and prognoses | MoLHSA/Expert group |
| Consider appropriateness and schedule non-pharmaceutical measures for public |  |  |  |  |  |  |  |  |  | Impact assessment, expert conclusions | MoLHSA/Expert group |
| Distribute initial stockpile of preparations |  |  |  |  |  |  |  |  |  | Prognoses and population data | MoLHSA |
| Refresh/focus information provided to public |  |  |  |  |  |  |  |  | Public broadcaster | Prepared information materials | Governmental sub-commission/ MoLHSA |
| Monitor and revise efficiency of initial procedures for disease case management and research |  |  |  |  |  |  |  |  |  | Operational feedback | MoLHSA/ local authorities |
| Monitor non-pharmaceutical measures targeted for public |  |  |  |  |  |  |  |  |  | Operational feedback | Implementing agencies |
| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  |  |  |  |  | Critical information/action | Primary source of information |
| WHO Phase 6 Alert level 3 in Georgia (Outbreak(s) in Georgia) | Governmental commission | MoLHSA |  |  |  | MoA |  | Local authorities | Other |  |  |
| Review threat assessment and assumptions used for planning |  |  |  |  |  |  |  |  |  | Operational feedback/ prognoses | Local authorities/ Expert group |
| Develop, implement additional mitigating measures, activate-annul relevant regulations |  |  |  |  |  |  |  |  |  | Operational feedback/ prognoses | Local authorities/ Expert group |
| Implement, monitor, evaluate and revise if needed the national response strategy |  |  |  |  |  |  |  |  |  | Operational feedback/ prognoses | Local authorities/ Expert group |
| Monitor and support response from local level healthcare services |  |  |  |  |  |  |  |  |  | Operational feedback/ prognoses | Local authorities/ Expert group |
| Revise/approve and use of antiviral treatment protocols |  |  |  |  |  |  |  |  |  | Operational feedback/ prognoses | WHO/Expert group |
| Assess and endorse the appropriateness of the decision on closing the schooling and schools |  |  |  |  |  |  |  |  | Ministry of Education | Existing data on pandemic impact | WHO/Expert group |
| Monitor functioning of key public services and infrastructure and business continuity |  |  |  |  |  |  |  |  | Ministry of Economic Development | Existing data on pandemic impact | Public and private agencies |
| Evaluate health management, morbidity and mortality data and adjust existing protocols |  |  |  |  |  |  |  |  |  | Existing data on pandemic impact | MoLHSA/ Expert group |
| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  |  |  |  |  | Critical information/action | Primary source of information |
| WHO Phase 6 Alert level 4 in Georgia (Widespread activity across Georgia) | Governmental commission |  | MoLHSA |  |  | MoA |  | Local authorities | Other |  |  |
| Review threat assessment, monitor disease spread and impact, review assumptions used for planning |  |  |  |  |  |  |  |  |  | Operational feedback/ prognoses | Local authorities/ Expert group |
| Monitor functioning of key public services and infrastructure and business continuity, and strengthen/weaken taken measures |  |  |  |  |  |  |  |  | Ministry of Economic Development | Existing data on pandemic impact | Public and private agencies |
| Assess the need for additional regulative and legislative authority |  |  |  |  |  |  |  |  | Other ministries and agencies | Operational feedback | Public and local governance agencies |
| Strengthen public information champagne/revise information materials |  |  |  |  |  |  |  |  |  | Operational feedback | Public and local governance agencies |
| Monitor and support response and functioning of healthcare services, ensure adequate number of medical personnel |  |  |  |  |  |  |  |  |  | Operational feedback | Health services, local governance agencies |
| Monitor adequate provision and logistics of antivirals, other pharmaceuticals and medical supplies |  |  |  |  |  |  |  |  |  | Operational feedback | Public and local governance agencies |
| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  |  |  |  |  | Critical information/action | Primary source of information |
| WHO Phase 6 Post-wave period | Governmental commission | MoLHSA |  |  |  | MoA |  | Local authorities | Other |  |  |
| Assess the threat of subsequent wave(s) and the response potential thereon |  |  |  |  |  |  |  |  |  | Epidemiological data, response experience and modeling | WHO/US and European CDCs/Expert panels |
| Assess healthcare threats of subsequent waves and prepare for potential impact |  |  |  |  |  |  |  |  |  | Epidemiological data, response experience and modeling | WHO/US and European CDCs/Expert panels |
| Discuss and evaluate development of new vaccines and possibilities for public vaccination alternatives |  |  |  |  |  |  |  |  |  | Information on vaccines | WHO/Global vaccine producers |
| Renew/maintain intensive procedures of epidemiological surveillance |  |  |  |  |  |  |  |  |  | Epidemiological data | WHO/International partners/MoLHSA |
| Assess the impact on healthcare system and commence the process for normal functioning of the system |  |  |  |  |  |  |  |  |  | Operational feedback | MoLHSA/ Healthcare services |

| Action trigger/cause | - Key responsible agency - Participating agency |  |  |  |  | Critical information/action | Primary source of information |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Post-pandemic period | Governmental commission | MoLHSA | MoA | Local authorities | Other |  |  |
| Evaluate general pandemic impact, plan for and implement measures for restoring infrastructure and normal functioning of services |  |  |  |  | Relevant agencies and ministries | Feedback/Assessment | All sources |
| Generalize, assess and use experience |  |  |  |  | Relevant agencies and ministries | Assessments | All sources |
| Routinely inform public and rehabilitate and support the communities and persons affected by pandemic |  |  |  |  | Relevant agencies and ministries | Clinical, operational and impact reports | All sources |

WHO – World Health Organization

MoLHSA – Ministry of Labor, Health and Social Affaires

CDC – Center for Disease Control

OIE – World Organization for Animal Health

Alert levels two and three may be declared in Georgia at WHO Phase 5 as well, in case if new pandemic virus is isolated and outbreak(s) take place in Georgia. In this case, response measures shall be based on the Phase 6 national alert levels list of actions.