Integrating HIV testing services in Primary Care in Tbilisi, Georgia

Rationale:

Support provided by the Global Fund to Fight AIDS, Tuberculosis and Malaria (GFATM) since 2004 enabled Georgia to make substantial progress in responding HIV, especially in the field of antiretroviral therapy (ART). Georgian service delivery model ensures high patient engagement in care, which in turn ensures universal access to ART for all. Since 2015 country implemented treat all policy. According to UNAIDS Georgia has the best ART coverage and viral suppression rates in the region of Eastern Europe and Central Asia (EECA), but has the worst diagnosis rate with only 48% of people living with HIV are aware of their diagnosis.

This significant gap in HIV diagnosis represents the main challenge in national HIV response, which compromises public health benefits of universal access to ART. Therefore, improving HIV diagnosis will be critical for reaching 90-90-90 targets towards ending the AIDS epidemic in Georgia.

Review of available data (GAM country reports, IBBS reports, surveillance data, and program reports)   indicates that HIV testing coverage of key populations at risk has been improving in recent past owing to expanding both GFATM and national programs. Although there is high coverage of persons with tuberculosis and viral hepatitis, overall provider initiated testing is implemented on a limited scale resulting in missed opportunities to test persons with various clinical conditions indicative of HIV (e.g. prolonged fever, respiratory infections, diarrhea, lymphadenitis, weight loss etc.).

In a previous study of factors associated with late HIV diagnosis, 22% of surveyed HIV positive persons reported referral to primary healthcare without receiving an HIV test despite the presence of conditions that should have triggered testing. This also leads to high rates of late diagnosis in the country, which is a significant problem.

Integrating HIV testing services in primary healthcare settings provides unique opportunity to extend the service to population segment previously not covered with interventions. This, along with scaling-up existing programs, will be crucial for achieving 90-90-90 targets.

Objective: The objective of the project is to improve HIV case detection through integrating HIV testing in primary care.

Tasks:		1. Testing for HIV clients of primary care clinics in Tbilisi

2. Rapid linkage to care and ART initiation of identified HIV positive persons

3. Contact tracing/partner referral of identified HIV positive persons.

4. Implement HIV Stigma reduction and HIV testing promotion media campaign

Approach:

Proposed project envisages integration of HIV testing services in 15 primary healthcare clinics (PHC). PC will be selected to ensure high geographic coverage. Project will reach-out persons aged 18 to 65 years old referring to selected PCs. For the pilot program three different testing strategies will be evaluated:

- Population at risk (at Specialized STI and proctology clinics)

- Offer free HIV testing to all PC clinics;

- Offering testing to everyone at PCs based on the questionnaire based self-risk assessment;

Locations for testing will be: Tbilisi 6 clinics. Kutaisi (3 clinics), Batumi (3 clinics) Zugdidi (3 clinics)

To ensure rapid and complete diagnosis we will apply reflex testing approach that is initial screening will be conducted using rapid antibody test, and if reactive the same specimen will be used for confirmatory analysis. All diagnosed persons will be counseled and referred to HIV clinical care services. In addition, all diagnosed persons will be interviewed and encouraged to referrer their partners for HIV testing.

Anticipated results:	1. Estimated 80,000 clients of PC will be tested for HIV

2. We anticipate that integration of testing services and partner referral will identify up to 200 additional cases of HIV.

Estimated number of Patients and Enrollment Plan

Each PC provides services to around 700-750 patients per month (10,500 - 11,250 persons per month by 15 PCs). As the duration of the project is 9 months, the total number of patients covered by PCs in 9 months will be 100,000 in average.  Taking into account projected response rate of 80%, estimated 80,000 clients will be tested for HIV at PCs in 9 months period.

Research conducted by Infectious Diseases, AIDS and Clinical Immunology Research Center showed approximately 0.4% detection of new cases of HIV among 3000 tested patients in multi profile clinic in Tbilisi. Accordingly, we assume that estimated 200 HIV infected persons will be identified through this project.

Rational

In the frame of National HIV/AIDS conference, December 2017 the initiative “End of AIDS epidemic in Georgia” was launched. The initiative which leads to achieve UNAIDS 90-90-90 targets was widely supported and outlined in the relevant declaration. This initiative will be reflected in the Georgian National HIV/AIDS Strategic Plan (NSPA) for 2019-2022 years and will be the one of the key points to identify 90% of HIV positives in the country.

This project will give unique opportunity for achieving the first target of 90-90-90 strategy which is the significantly underachieved (diagnoses rate was about 48% of estimated number of PLHIV by the end of 2017).

The project will be integrated with ongoing hepatitis C screening program at PC facilities within the National HCV Elimination Program and will be supported by the stigma reduction media campaign to increase the publics’ interest and uptake of testing.

Media Campaign

Building on the positive experience gained from Hep C elimination program in Georgia, the CCM and the Ministry of Labour, Health and Social Affairs would like to implement population based anti-HIV stigma media campaign using various vectors of the media, including TV channels, social media (Facebook), street billboards and posters. It will have wide geographic coverage as well. The technical request will include development of a media campaign plan that will be discussed and agreed with all key stakeholders active in the field of HIV.

The campaign will be aligned with PC-based HIV screening program will largely benefit from this campaign, TV channels are identified through consolidated state tender and only these channels will be contracted and used within the proposed anti-stigma and HIV testing promotion campaign.  The TV and social media will be used to spread the relevant messages and broadcast developed TV spots.

Requested amount 428,000 USD (including Media Campaign for 100,000 USD)

The table 1. provides the Details of the Media Campaign Plan (Prices are the Subject to change based on the Tender Procurement)

Table 1

| N | Activity | Description | Deliverables | Time-frames | Estimated cost in USD |
| --- | --- | --- | --- | --- | --- |
| 1 | Planning and development/printing |  |  | 01.05.2018 - 30.06.2018 | 30,000 |
| 1.1. | Development of the media campaign plan | Detailed list of media products and dissemination plan | Media Plan, Dissemination Plan M&E Plan | 31.05.2018 | 3000 |
| 1.2. | Branding | - Development of main messages, slogans, logo and brending | - Minimum 5 messages Minimum 1 Slogan Minimum 1 logo | 31.05.2018 | 1500 |
| 1.3. | Development of Banners for external show cases and billboards and printing | Development of thematic banners in agreement with PR | At least 5 banners Dimensions: 6mx3m | 30.06.2018 | 1500 |
| 1.4. | Development and printing of posters | Development of thematic posters in agreement with PR | -At least 5 types, 5000 copies (1000 copies each) | 30.06.2018 | 1500 |
| 1.5. | Development of video spots | 2 types of 3 video spots should be developed: a) for TV and b) for internet media. Content and visual should be agreed with PR | TV sports – 3 types, 25 sc Internet sports – 3 types, 10sc | 30.06.2018 | 21000 |
| 1.6. | Development of internet banners | Development of internet banners for placement in popluar web pages and in social media | - at least 10 banners | 30.06.2018 | 1500 |
| 2. | Implementation of Media Campaign |  |  |  | 70,000 |
| 2.1. | Placement of External Banners | Total number 25 Geographic distribution: In Tbilisi – 20 Vake-Saburtalo 4 Old Tbilisi 4 Didube Chughureti 4 Gldani Nadzaladevi 4 Isani-samgori 4 - 5 Banners in Batumi - 5 Banners in Zugdidi - 5 –Banners in Kutaisi | Duration 3 months Dimensions: 600x300სმ; | 01.08.2018 - 31.10.2018 | 15000 |
| 2.2. | Posters Presentation | Posters should be placed at the following locations: Medical Facilities Educational facilities Bars and Night Clubs | Geographic locations: Tbilisi, Batumi, Zugdidi and Kutaisi 2000 in Tbilisi, 1000 in each region | 01.07.2018 - 01.12.2018 | 3000 |
| 2.3. | Broadcast of video sports through TV Channels | Video Spots should be proadcasted through the TV channels based on the TMI (Tri Media Intelligence) and/or TVMR rating 1 and 2. TV Channels should have country-wide coverage At least 75% should be broadcasted during the prime time | Duration 3 months At least 300 broadcast events per TV Channel, total 1800 events | 01.09.2018 - 30.10.2018 | 23000 |
| 2.4. | Internet broadcase of video spots in Pre-Roll advertisement format | Internet broadcast web-pages: www.imovies.ge www.adjaranet.ge www.myvideo.ge www.youtube.com - | - Pre-Roll advertisement duration 3 months ; 3 types of spots. | 01.09.2018 - 30.10.2018 | 3,000 |
| 2.5. | Internet banners placement | List of the web-sites www.jobs.ge www.mymarket.ge www.myauto.ge www.imovies.ge www.adjaranet.ge www.facebook.com - | Duration 5 months Types of banners 10 | 01.07.2018 - 01.12.2018 | 3000 |
| 2.6. | Organization of thematic talk shows | Talk Show should be organized at the TV channel TMI (Tri Media Intelligence) and/or TVMR rating 1 and/or 2 within the well known Medical, Public, Educational or Political shows. | At least 2 Talks Shows | 01.09.2018 - 01.12.2018 | 20,000 |
| 2.7. | Implementing viral media campaign through social media | Campaign should include celebrities and public figures, content should be agreed with PR | At least 1 campaign, at least 1000 users should participate (#likes) | 01.11.2018 - 30.11.2018 | 3,000 |

UNAIDS. Ending AIDS: Progress towards 90-90-90 targets. Global AIDS Update 2018.

Chkhartishvili N, Rukhadze N, Sharvadze L, Gabunia P, Gamkrelidze A, Tsertsvadze T. Factors associated with late HIV diagnosis in Georgia: Survey report. Infectious Diseases, AIDS and Clinical Immunology Research Center. Tbilisi, 2012.

Chkhartishvili N, Chokoshvili O, Bolokadze N, Tsintsadze M, Sharvadze L, Gabunia P, Dvali N, Abutidze A, Tsertsvadze T. Late presentation of HIV infection in the country of Georgia: 2012-2015. PLoS One. 2017 Oct 30;12(10):e0186835.