OST Programs

- Mobile OST Program – Duration 10 months

Requested amount 230,000 USD

The amount is requested to pilot mobile OST program. Three mobile cars (one car will be in reserve) will be procured and adapted for the OST Program needs. The Grant Program will cover all costs of the program operation (salaries of mobile unit, equipment, drugs and supplies, gasoline, security, insurance, etc.)

There will be two routes that will cover Kakheti region and Kvemo - Kartli regions. Estimated number of beneficiaries per route – 200, total up to 500

CT information requests:

- Could you please explain how the target of 200 per route was estimated?

- Could you please provide the implementation plan for this initiative? Could you please explain why you plan to procure 3 vans for 2 regions and what it means to have one in reserve?

- We note that the list of requested costs include drugs. Please clarify which drugs?

- Please clarify what is the government co-financing plan for this programme component? As discussed, our expectation is that the government will purchase OST drugs, while our support may extend to financing the start-up of this initiative. FYI, following our recent mission, we initiated an email exchange with Deputy MOH on finding cheaper methadone procurement options for Georgia. Could you please follow up?

- Please clarify which equipment costs you are seeking support for?

PRs response:

Estimated number of beneficiaries is based on the current clients of OST center coming every day from the regions that we target with mobile OST program; on the interviews of the narcologist working in the regions and representatives of needle and syringe program that advocate for mobile OST in these two regions. For instance, as for today in Kvemo Kartli region to Tbilisi OST sites come 81 clients on daily base, who report that on the route that was developed with their involvement about 200 patients would like to get enrolled in the program. To be on the safe side and considering that this is a pilot program, we presented a modest target of 200 patients by the end of 6 months of the pilot. The same approach was used for the second target region.

Implementation plan includes: Preparation phase - working with the Ministry of Labour, Health and Social Affairs to change the regulations in support of a mobile OST program; the same time preparation of a detailed protocol will be conducted; medical personnel and security staff will be trained, Mobile OST stop spots will be defined and agreed with local municipalities; PWID peers and outreach workers will be used to spread the information about the Pilot program and invite for registration.

Procurement of mobile cares and inventory;

Third car was requested in order to have in reserve if one of two cars will be stopped due to technical reasons as the program should run on a daily base and patients can’t miss the daily doses.

- Methdaone will be supplied by the State;

- equipment includes drug dispersing pipettes, computers, security cameras, etc.)

- Prison OST Program – Duration 10 months

Requested amount 70,000 USD

The long term (maintenance) substitution treatment program will be initiated at the Prison N17 in Rustavi. The amount will cover minor renovation, equipment, security, observation cameras, HR, drug and supplies cost. The estimated number of prisoners to be enrolled in the program by the end of the implementation period – 150.

CT information requests:

- Could you please explain how the target of 150 patients was established?

- Could you please provide the implementation plan for this initiative? Could you please confirm that the programme would provide substitution therapy, not detoxification.

- Please clarify what is the government co-financing plan for this programme component? As discussed, our expectation is that the government will purchase OST drugs, while our support may extend to financing the start-up of this initiative. FYI, following our recent mission, we initiated an email exchange with Deputy MOH on finding cheaper methadone procurement options for Georgia. Could you please follow up?

- We note that the list of requested costs include drugs. Please clarify which drugs?

- Please clarify which HR and minor renovation costs you are seeking

PRs response:

Number of beneficiaries: During a year about 800-1000 persons go through methadone detoxification program in prisons, out of which about 85% are those OST patients who were enrolled in outside (civic) OST programs and who would like to continue substitution (maintenance) treatment in prisons as well. In the proposed prison N8 at the moment we have 102 prisoners, from which 84 were part of the OST before imprisonment. We will start with 150 patients but the facility can accommodate more based on the needs. It is a pilot program that can be expanded to other prisons where at the moment we have only long term methadone detox programs.

Preparation period will include development of relevant infrastructure to meet the regulation requirements such as have a separate unit with drug disbursing window, storage with metal doors, security and monitoring cameras, alarm system). The preparation phase will include development of a detailed guide and SOPs, training of personnel (medical) and security people.

Penitentiary department will cover cost of utilities and cleaning of the facility. Methadone will be provided from the State OST Program (two times delivery per year).

In minor renovation cost we include development of relevant infrastructure to meet the state regulations for OST unit operations (disrobed above).