- Continuation of PrEP Program – Duration 10 months

Requested amount 140,000 USD

The amount is requested to ensure continuation of the current pilot program as well as to expand it to regions (Batumi, Adjara and Kutaisi, Imareti). The cost inputs and categories will be the same as in the current pilot program.

The estimated number of beneficiaries by July 1, 2019 - 200

CT information requests: We are pleased to see that you are planning the further roll-out of the PrEP programme. We would like to better understand the following aspects of this second phase:

- Could you please clarify whether you are planning to use the same approaches as in the first phase or are there any changes in the implementation plan.

- Could you please clarify how the targets were estimated? Are the 200 beneficiaries additional to the current 100 planned to be reached. Could you please explain the planned costs vs. targets?

- What is the reason to wait until July to start the roll-out of the next phase of the programme?

Could you please clarify whether you are planning to use the same approaches as in the first phase or are there any changes in the implementation plan.

The proposed amount is requested to ensure the continuation of the PrEP intervention initiated for MSM community in September 2017. For the next 10 month implementation period no changes will be introduced in the clinical protocol of the program and the approach of the daily PrEP will be the main implementation scheme, although the demand for the daily PrEP will be investigated among the community members and if the need will be identified, during this 10 months the community and the clinical experts will elaborate relevant protocol for so called On-Demand PrEP.

Latest research data proves that maximum rectal tissue concentration is reached after only 2 doses of TDF/FTC, thus on-demand PrEP can be considered as an effective option. Programme observation shows that people have “seasons of risk”, so introduction of intermittent PrEP, in the sense of taking breaks from PrEP when people are at no risk, but being able to start using it again if they start being at risk again, is considered. For example In the IPERGAY trial, the most common sort of pattern was a few months on, a couple of months off, then back again. It should not be regarded as a failure of adherence if the person judges that they do not need PrEP for a while.

Based on the project data there yet was no single case, with kidney problems, related to creatinine clearance rates. As the median age of enrolled PrEP participants is 29 years (with youngest 19 years and oldest 42 years old), while expected age of kidney related problems that uptake of PrEP can negatively affect is 49 or older, we will rethink the clinical eligibility criteria for enrolment. It will simplify the procedures, however we still will provide close monitoring of creatinine clearance in accordance to clinical protocol.

As the community organization has identified the provision of the PrEP clinical services at the Clinical facility only as barrier for the program implementation during the next implementation phase of the PrEP (10 months) we will bring the clinical services closer to the community with having on duty physician at the CBO site and organizing blood samples transportation logistics for laboratory testing.

Approach of same day PrEP prescription and provision is also considered to be introduced. For now there is possible a several days interval between screening for eligibility and prescription/provision of PrEP medications.

The issue is, what happens if someone has an HIV risk exposure in between taking their test and starting PrEP – and keeps on doing it. In this case to postpone enrolment is not an option, as long as person is at extremely high risk. Thus taking into consideration best practises of some PrEP trials, e.g. PROUD Study. To provide people PrEP on their first appointment: person walked out of the clinic with PrEP the same day he/she took the test.

It is planned to change the approach of prioritising purely in terms of age. As far as individual people are concerned, the association of age with risk is dependent entirely on other variables – number of partners, condom use, relationship status, etc. There are some highly at-risk older men, e.g. ones just out of a relationship or new to exploring their sexuality.

As it was initially considered it is planned to increase role of community organization(s), we consider to transfer PrEP medication prescription and provision in the community organization.

Use of an online approaches for PrEP provision is widely considered. First of all assessment of risk behaviour and eligibility criteria can be done online, by people themselves. Example:

http://www.ispreprightforme.com/

A long as most of individuals have a discomfort and identify frequent visits as a barrier, it is planned to use online approaches for risk reduction counselling, adherence counselling and other social support interventions.

-         Could you please clarify how the targets were estimated? Are the 200 beneficiaries additional to the current 100 planned to be reached. Could you please explain the planned costs vs. targets?

200 beneficiaries are total number. It means that 100 additional participants, will be enrolled in next phase. However if we will consider on-demand PrEP than estimated numbers will be different, taking into account that enrolled individual will not undergo all visits and services considered for PrEP uptake during a whole year, and one person can be in and out for several times.

-         What is the reason to wait until July to start the roll-out of the next phase of the programme?

Existing ongoing PrEP pilot projects’ timeframe is August 2017 - June 2018. So the reason behind starting second phase since July is to wait until the end of the project, to have possibility to fully consider all observations, challenges and achievements and plan next phase accordingly.

Supporting evidences for On-Demand PrEP:

1. European AIDS Clinical Society PrEP Guidelines that recommends on-demand PrEP.

2. Clinical trials conducted in France and Canada Ipergay, with 86% efficacy https://www.avac.org/trial/ipergay

http://www.bmj.com/content/358/bmj.j3619/rapid-responses

https://www.ncbi.nlm.nih.gov/pmc/articles/PMC5095697/

http://www.thelancet.com/journals/lanhiv/article/PIIS2352-3018(17)30088-7/abstract

3. On-demand PrEP is used in France, Canada, England, below is a detailed guide for this approach. https://www.iwantprepnow.co.uk/how-to-take-prep