Ministry of the Internally Displaced People from the Occupied Territories, Labour, Health and Social Affairs of Georgia

Hepatitis C Elimination Program

Monthly Progress Report- April 2020

Contents

Introduction	2

1	Statistics	2

1.1	Georgia Hepatitis C Elimination Program Care Cascade, April 28, 2015  –  April 30, 2020	2

2	Update on programmatic activities	3

2.1	Information about screening activities	4

2.2	Information about drugs	5

2.3	Other Activities	5-6

# Introduction

In April 2016, The Government of Georgia and the company "Gilead" signed a long-term agreement on the continuous provision for zero price of the new generation of hepatitis C medicines by Gilead Science Inc., until the elimination of hepatitis C in Georgia.

In August 2016, a long-term strategy for elimination of hepatitis C (2016-2020) was developed to achieve the ultimate goal of eliminating the hepatitis C. Strategy sets forth the following targets, to be reached by 2020:

- 90% of HCV infected persons will be tested for their infection,

- 95% of people with chronic infection will receive treatment, and

- 95% of persons receiving treatment will be cured of HCV

This report reflects the Hep C elimination program progress in April 2020. The report was prepared by the Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs of Georgia in collaboration with the National Center for Disease Control and Prevention.

# Statistics

## Georgia Hepatitis C Elimination Program Care Cascade, April 28, 2015 – April 30,  2020

# Update on programmatic activities

## Information about screening activities

 Total number of registered screening is 3 826 066

  Total number of positive screening among the registered ones is 179 153 (4.68%)

  Distribution by age and gender among the positive screenings (figures 1 and 2):

## 2.2. Figure 1. Number of Individuals screened on Hep C and confirmed with the disease per age categories, April 28, 2015 – April 30, 2020

## Figure 2: Number of individuals screened and found positive on Hep C per gender, April 28, 2015 – April 30, 2020

## Information about drugs (April 28, 2015 – April 30, 2020)

Total number of disbursed Sovaldi bottles: 39 478

Sovaldi bottles delivered to service Providers:  34 586

Sovaldi bottles donated to the Republic of Belarus: 1 500

Sovaldi bottles donated to the Republic of Armenia: 3 000

Sovaldi bottles remaining in central stock: 393 (validity period is expired, since sovaldi regimens are almost no longer used for treatment in practice)

Total number of disbursed Harvoni bottles: 173 440

Harvoni bottles delivered to service Providers:  166 294

Harvoni bottles remaining in central stock: 9 (+7137 expired as of April 30th , 2018)

Total number of disbursed Epclusa bottles: 10 976

Epclusa bottles delivered to service Providers:  10 976

Epclusa bottles remaining in central stock:  0

Total number of disbursed MyHepAll bottles: 24 003

MyHepAll bottles delivered to service Providers:  14 147 MyHepAll bottles remaining in central stock:  9856

## Information about Elimination Program Data Management System

- Technical support of screening “STOP C” and Hepatitis C treatment systems is ongoing.

## Other Activities

Strategic Plan for HCV Elimination in Georgia 2015-2020

The draft Strategic Plan for HCV Elimination in Georgia 2015-2020 to support the development of Georgia’s updated Strategy or Implementation Plan for the Elimination of Hepatitis C and B in Georgia 2021-2025 is being prepared. Program monitoring and evaluation indicators will also be updated with support of CDC and other stakeholders. The updated documents are supposed to be published in December 2020.There are several topics to be agreed with stakeholders, including:

- Structure of the template

- Strategic objectives and Sections identified

- Including Hepatitis B and possible integration with Universal Health Care

- Workgroups

- Roles and responsibilities defined: who will lead each section?

- HCV elimination goal won’t be reached by 2020

- Recalibration exercise considering 2015 serosurvey prevalence confidence intervals

- Targets to be revised

- Who will be responsible for revising targets?

CDC shared suggested structure to be followed and template for strategy one (Promote advocacy, awareness and education, and partnerships for HCV-associated resource mobilization) with Ministry and NCDC for their approval.

Annual report

CDC was assisting in writing the annual report for the HCV Elimination Program based on monitoring and evaluation indicators and data analysis. The entire annual report was shared with NCDC, clinical groups, and leads for each section. After receiving the feedback from each responsible individual the entire document will be shared with the Ministry.

Communication with US Embassy on HCV

CDC Tbilisi team is attending regular monthly meetings with DCM sharing updates on the HCV elimination program.

University of Bristol project

In 2019, the scientific committee approved the proposal “Learning lessons from Georgia -using economic modeling to determine optimum screening and linkage-to-treatment strategies for achieving high treatment coverage in Eastern Europe and Central Asia”.  It was agreed that the working group members would consist of investigators from each of the 4 clinics in Tbilisi, NCDC, MoH, and CDC. The proposal was submitted to the Gilead Science Inc. and approved for funding. The launch was planned for April 2020, though considering the evolving situation around COVID-19, the impact on travel, and current unavailability of main stakeholders, the Bristol team will be discussing with Gilead postponing of the launching of the study.