## All Product
BLUE TACTICAL PLAN -- ALL PRODUCT
District | Product | Code | Title | Script Draft 1 Due to Full Pod | DCCC and Pod Feedback on Script Draft 1 | Script Draft 2 Due | Research Signoff and Sent to Legal for Feedback/Sample Approved | Legal Feedback Due | DCCC Incorprates Legal Feedback and Their Final Feedback | Script Draft 3 Due | DCCC Gives Final Signoff of Script/Poll | Ad Received by Full Pod | DCCC Sends Ad to Legal, Gives Feedback to Media Consultant | Final Ad Approval and Approval to Ship | Field/Ship Date | Toplines Due | Crosstabs Due | Air Date | Polling Memo Due | Individual Level Responses Due
NH-01 | Poll | DC316-NH01-P01 | Benchmark | 2016-08-26 | 2016-08-31 | 2016-09-02 | 2016-09-05 | 2016-09-08 | 2016-09-08 | 2016-09-09 | 2016-09-13 |  |  |  | 2016-09-14 | 2016-09-17 | 2016-09-18 |  | 2016-09-20 | 2016-09-20
NH-02 | Poll | DC316-NH02-P01 | Benchmark | 2016-09-02 | 2016-09-06 | 2016-09-08 | 2016-09-11 | 2016-09-14 | 2016-09-14 | 2016-09-15 | 2016-09-16 |  |  |  | 2016-09-18 | 2016-09-21 | 2016-09-22 |  | 2016-09-24 | 2016-09-24
IA-03 | Poll | DC316-IA03-P01 | Benchmark | 2016-07-15 | 2016-07-19 | 2016-07-21 | 2016-07-24 | 2016-07-27 | 2016-07-27 | 2016-07-28 | 2016-07-29 |  |  |  | 2016-07-31 | 2016-08-03 | 2016-08-04 |  | 2016-08-06 | 2016-08-06
NY-11 | Poll | DC316-NY11-P01 | Benchmark | 2016-07-29 | 2016-08-02 | 2016-08-04 | 2016-08-07 | 2016-08-10 | 2016-08-10 | 2016-08-11 | 2016-08-12 |  |  |  | 2016-08-14 | 2016-08-17 | 2016-08-18 |  | 2016-08-20 | 2016-08-20
MA-09 | Poll | DC316-MA09-P01 | Benchmark | 2016-09-02 | 2016-09-06 | 2016-09-08 | 2016-09-11 | 2016-09-14 | 2016-09-14 | 2016-09-15 | 2016-09-16 |  |  |  | 2016-09-18 | 2016-09-21 | 2016-09-22 |  | 2016-08-24 | 2016-08-24
NJ-02 | Poll | DC316-NJ02-P01 | Benchmark | 2016-09-02 | 2016-09-06 | 2016-09-08 | 2016-09-11 | 2016-09-14 | 2016-09-14 | 2016-09-15 | 2016-09-16 |  |  |  | 2016-09-18 | 2016-09-21 | 2016-09-22 |  | 2016-08-24 | 2016-08-24
NJ-03 | Poll | DC316-NJ03-P01 | Benchmark | 2016-07-15 | 2016-07-19 | 2016-07-21 | 2016-07-24 | 2016-07-27 | 2016-07-27 | 2016-07-28 | 2016-07-29 |  |  |  | 2016-07-31 | 2016-08-03 | 2016-08-04 |  | 2016-08-06 | 2016-08-06
MI-06 | Poll | DC316-MI06-P01 | Benchmark | 2016-07-29 | 2016-08-02 | 2016-08-04 | 2016-08-07 | 2016-08-10 | 2016-08-10 | 2016-08-11 | 2016-08-12 |  |  |  | 2016-08-14 | 2016-08-17 | 2016-08-18 |  | 2016-08-20 | 2016-08-20
VA-10 | Poll | DC316-VA10-P01 | Benchmark | 2016-07-15 | 2016-07-19 | 2016-07-21 | 2016-07-24 | 2016-07-27 | 2016-07-27 | 2016-07-28 | 2016-07-29 |  |  |  | 2016-07-31 | 2016-08-03 | 2016-08-04 |  | 2016-08-06 | 2016-08-06